## Cash Flow Forecast
PROJECT BUDGET - HCRE WELLNESS CENTER
2026-10-21
Category / Sub-category | Type |  |  |  |  | 2026-07-01 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27
REVENUE | Budget | Total to Date | Cost To Complete | Revised Budget | Variance | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Life Right deposits received | 33480000 | 0 | 0 | 0 | 33480000
Other income |  | 0 | 0 | 0
Total Revenue | Total | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT COSTS | Budget | Total to Date | Cost To Complete | Revised Budget | Variance | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Professional fees – Architect (Elise / Leanor) | 147500 | 99500 | 48000 | 147500 | 0 | 37250 | 62250 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Designs & 3D renders (ARC wellness 1) | 14250 | 14250 | 0 | 14250 | 0 |  | 14250
- Designs & 3D renders (ARC wellness 2) | 14250 | 14250 | 0 | 14250 | 0 | 14250
- Designs - layouts, site plan, elevaltions, artist impressions ( ARC BKA 1) | 23000 | 23000 | 0 | 23000 | 0 | 23000
- Municiple drawing preperation & Approval (LVG 10) | 96000 | 48000 | 48000 | 96000 | 0 |  | 48000 |  |  |  | 48000
Professional fees – Engineer | 114998.85 | 38332.95 | 76665.9 | 114998.85 | 0 | 0 | 38332.95 | 0 | 0 | 38332.95 | 0 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
- Civil Engineer |  | 0 | 0 | 0
- Structural Engineer |  | 0 | 0 | 0
- Electrical / Mechanical Engineer |  | 0 | 0 | 0
- - Johan Erwee (3147) | 114998.85 | 38332.95 | 76665.9 | 114998.85 | 0 |  | 38332.95 |  |  | 38332.95 |  |  | 38332.95
Professional fees – Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Land Surveyor |  | 0 | 0 | 0
- Attorney |  | 0 | 0 | 0
- Auditors |  | 0 | 0 | 0
- PM |  | 0 | 0 | 0
Municipal fees & contributions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- NHBRC |  | 0 | 0 | 0
- Plann Approval |  | 0 | 0 | 0
- Sewage |  | 0 | 0 | 0
- Water |  | 0 | 0 | 0
- Electrical |  | 0 | 0 | 0
-Storm Water |  | 0 | 0 | 0
- Rates and Taxes |  | 0 | 0 | 0
Site preparation & earthworks | 149452 | 99726 | 49726 | 149452 | 0 | 0 | 50000 | 0 | 49726 | 0 | 49726 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Site Clearance |  | 0 | 0 | 0
- Fencing | 99452 | 49726 | 49726 | 99452 | 0 |  |  |  | 49726 |  | 49726
- Security |  | 0 | 0 | 0
- Casual Labour | 50000 | 50000 | 0 | 50000 | 0 |  | 50000
External infrastructure |  | 0 | 0 | 0
Internal infrastructure & parking |  | 0 | 0 | 0
Top structures – Units |  | 0 | 0 | 0
Top structures – Wellness Centre |  | 0 | 0 | 0
FF&E |  | 0 | 0 | 0
Marketing & sales costs |  | 0 | 0 | 0 |  |  | 0
Company Administrative Cost |  | 0 | 0 | 0
Contingency
Total Project Costs | 411950.85 | 237558.95 | 174391.9 | 411950.85 | -5.8208e-11 | 37250 | 150582.95 | 0 | 49726 | 38332.95 | 97726 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
FUNDING SOURCES, DEBT BALANCES & CASH RECONCILIATION
Period | Input / note | Actual | Forecast | Total | Closing / check | 2026-07-01 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27
Status | Grey cells = formula |  |  |  | Yellow cells = input | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Project costs (linked) |  | 237558.95 | 174391.9 | 411950.85 |  | 37250 | 150582.95 | 0 | 49726 | 38332.95 | 97726 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
Manual cost adjustment |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cash requirement |  | 237558.95 | 174391.9 | 411950.85 |  | 37250 | 150582.95 | 0 | 49726 | 38332.95 | 97726 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
RMH MEZZANINE | Capital facility | 10000000 | Interest capitalised separately
Opening capital balance | [5 empty] | 0 | 37250 | 187833 | 187833 | 237559 | 275892 | 373618 | 373618 | 411951 | 411951 | 411951 | 411951 | 411951
Capital utilisation / drawdown |  | 237559 | 174392 | 411951 |  | 37250 | 150583 | 0 | 49726 | 38333 | 97726 | 0 | 38333 | 0 | 0 | 0 | 0 | 0
Capital repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing capital balance |  |  |  |  | 411951 | 37250 | 187833 | 187833 | 237559 | 275892 | 373618 | 373618 | 411951 | 411951 | 411951 | 411951 | 411951 | 411951
Remaining capital facility |  |  |  |  | 9588049 | 9962750 | 9812167 | 9812167 | 9762441 | 9724108 | 9626382 | 9626382 | 9588049 | 9588049 | 9588049 | 9588049 | 9588049 | 9588049
Interest rate p.a. |  |  |  |  | 11.75% | 11.5% | 11.5% | 11.5% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75% | 11.75%
Interest charged for month |  | 5139.7269 | 33366.4554 | 38506.1823 |  | 178.4896 | 1078.5227 | 1800.0663 | 2082.6483 | 2513.7705 | 3179.8927 | 3658.3429 | 3846.0149 | 4033.6869 | 4033.6869 | 4033.6869 | 4033.6869 | 4033.6869
Opening interest balance | [5 empty] | 0 | 178.4896 | 1257.0123 | 3057.0785 | 5139.7269 | 7653.4974 | 10833.3901 | 14491.733 | 18337.7479 | 22371.4348 | 26405.1217 | 30438.8085 | 34472.4954
Interest repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing interest balance |  |  |  |  | 38506.1823 | 178.4896 | 1257.0123 | 3057.0785 | 5139.7269 | 7653.4974 | 10833.3901 | 14491.733 | 18337.7479 | 22371.4348 | 26405.1217 | 30438.8085 | 34472.4954 | 38506.1823
Total RMH balance |  |  |  |  | 450457.1823 | 37428.4896 | 189090.0123 | 190890.0785 | 242698.7269 | 283545.4974 | 384451.3901 | 388109.733 | 430288.7479 | 434322.4348 | 438356.1217 | 442389.8085 | 446423.4954 | 450457.1823
OTHER DEBT | Opening balances entered in first month
Opening capital balance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital utilisation / drawdown |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing capital balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest rate p.a. |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Interest charged for month |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening interest balance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing interest balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total other debt balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OTHER EQUITY | No interest assumed
Opening equity balance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity contributions / utilisation |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity repayments / distributions |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing equity balance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH RECONCILIATION | Monthly funding source allocation
Opening cash on hand |  |  |  |  | 0.15 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
RMH capital utilisation |  | 237559 | 174392 | 411951 |  | 37250 | 150583 | 0 | 49726 | 38333 | 97726 | 0 | 38333 | 0 | 0 | 0 | 0 | 0
Other debt utilisation |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity utilisation |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total new funding |  | 237559 | 174392 | 411951 |  | 37250 | 150583 | 0 | 49726 | 38333 | 97726 | 0 | 38333 | 0 | 0 | 0 | 0 | 0
Total cash available |  |  |  |  | 0.15 | 37250 | 150583 | 0.05 | 49726.05 | 38333.05 | 97726.1 | 0.1 | 38333.1 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
Project costs |  | 237558.95 | 174391.9 | 411950.85 |  | 37250 | 150582.95 | 0 | 49726 | 38332.95 | 97726 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
Manual cost adjustment |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RMH capital repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RMH interest repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other debt capital repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other debt interest repayments |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity repayments / distributions |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cash utilisation |  | 237558.95 | 174391.9 | 411950.85 |  | 37250 | 150582.95 | 0 | 49726 | 38332.95 | 97726 | 0 | 38332.95 | 0 | 0 | 0 | 0 | 0
Closing cash on hand |  |  |  |  | 0.15 | 0 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
Funding check | Closing cash should remain non-negative |  |  |  | 0.15 | 0 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15